## excel
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 44.9 | 21.1 | 39.3
Planned Time | 0.3875 |  | 1899-12-31 09:25
Actual Tiempo |  | 0.375 | 1899-12-31 22:37
CPI (Cost-Performance Index) |  |  | 0.72
% Reuse | 0% | 0% | 0%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 9.13 | 0 | 8.18
Total Defects/KLOC or equivalent | 17 | 10.5 | 16.4
Yield % | 48.1% | 100% | 51.7%
Code Review Rate | 2355 | 407 | 1549
% Appraisal COQ | 2.92% | 8.7% | 4.04%
% Failure COQ | 12.8% | 16.1% | 13.5%
COQ A/F Ratio | 0.23 | 0.54 | 0.3
PQI | 0 | 0.05 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 02:11 AM el 5/04/2017